## Plan
Phase | Item | What | Status
1 Core | 1.1 | Monorepo | done
1 Core | 1.2 | Contracts | done
1 Core | 1.3 | Config (defineConfig, loadConfig, resolveConfig, validateConfig) | next
1 Core | 1.4 | Execution / test context
1 Core | 1.5 | Lifecycle, extensions, fixtures
1 Core | 1.6 | Logging + errors
1 Core | 1.7 | Artifacts + results
1 Core | 1.8 | Core tests + reference consumer
1 Core | 1.9 | Thin Playwright (native, no action wrappers)
1 Core | 1.10 | Thin API
2 CLI | 2.1 | qakit init / qakit version
2 CLI | 2.2 | Changesets / release
2 CLI | 2.3 | qakit upgrade (later, if needed)
3 Pilot | 3.1 | First real team — onboard, CI, first real run
Cap: 8 hours per week. Holiday 21.12.2026 – 03.01.2027: 0 hours.

## Log
Week | From | To | Work | Hours | Meetings | Notes
W0 | 2026-08-17 | 2026-08-23 | Discovery | 8 | 3 client meetings | Greenfield
W1 | 2026-08-24 | 2026-08-30 | 1.0 Alignment, 1.1 Monorepo, 1.2 Contracts | 8 |  | Docs + code on main
W2 | 2026-08-31 | 2026-09-06 | 1.3 Config
W3 | 2026-09-07 | 2026-09-13 | 1.3 Config finish
W4 | 2026-09-14 | 2026-09-20 | 1.4 Execution / test context
W5 | 2026-09-21 | 2026-09-27 | 1.5 Lifecycle start
W6 | 2026-09-28 | 2026-10-04 | 1.5 Lifecycle finish
W7 | 2026-10-05 | 2026-10-11 | 1.6 Logging + errors start
W8 | 2026-10-12 | 2026-10-18 | 1.6 Logging + errors finish
W9 | 2026-10-19 | 2026-10-25 | 1.7 Artifacts + results start
W10 | 2026-10-26 | 2026-11-01 | 1.7 Artifacts + results finish
W11 | 2026-11-02 | 2026-11-08 | 1.8 Core tests + consumer start
W12 | 2026-11-09 | 2026-11-15 | 1.8 Core tests + consumer finish
W13 | 2026-11-16 | 2026-11-22 | 1.9 Thin Playwright start
W14 | 2026-11-23 | 2026-11-29 | 1.9 Thin Playwright continue
W15 | 2026-11-30 | 2026-12-06 | 1.9 Thin Playwright finish
W16 | 2026-12-07 | 2026-12-13 | 1.10 Thin API start
W17 | 2026-12-14 | 2026-12-20 | 1.10 Thin API finish
W18 | 2026-12-21 | 2026-12-27 | Holiday | 0
W19 | 2026-12-28 | 2027-01-03 | Holiday | 0
W20 | 2027-01-04 | 2027-01-10 | 2.1 CLI init / version
W21 | 2027-01-11 | 2027-01-17 | 2.2 Changesets / release
W22 | 2027-01-18 | 2027-01-24 | 3.1 Pilot onboard
W23 | 2027-01-25 | 2027-01-31 | 3.1 Pilot pairing + first run
W24 | 2027-02-01 | 2027-02-07 | Pilot holes / upgrade if needed
Total hours
Yellow cells: type hours / meetings / notes yourself. Meetings example: 03.09. 1h client — config review